## SUPS-WRKS-NCONS
PROCUREMENT PLAN FOR GOODS, WORKS AND NON CONSULTANCY SERVICES - FOR SUBMISSION TO TREASURY, PPDA and PUBLICATION
Procuring and Disposing Entity: DEPOSIT PROTECTION FUND
Financial Year: 2025/26
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) - Not Applicable |  |  |  |  | Source of funding | Procurement method | Procurement Category | Contract Type | PRE-QUALIFICATION (Yes or No) | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme (Local Providers, Special Interest Groups) | INVITATION AND AWARD OF BIDS |  |  |  | Contract signing date | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [7 empty] | Bid invitation date | Bid closing/ Opening date | Approval evaluation report date | Award notification date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22
1 | Supply of a Motor Vehicle | UGX | 350000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-23 | 2025-08-12 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2026-02-27
2 | Additional Media Advertising and Monitoring Services | UGX | 350000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Non-Consultancy Services | Framework Contracts | No | Yes | Local Providers | 2025-09-19 | 2025-10-10 | 2025-11-07 | 2025-11-14 | 2025-11-28 | 2028-11-27
3 | Provision of Workman’s Compensations | UGX | 280000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-30 | 2025-11-12 | 2025-12-10 | 2025-12-17 | 2025-12-31 | 2028-12-30
4 | Team building and end of year party activities | UGX | 270000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-09-29 | 2025-10-10 | 2025-11-06 | 2025-11-13 | 2025-11-28 | 2025-12-19
5 | Oracle licences for the HIA system (Database Standard Edition, Weblogic server Standard edition, Oracle Forms & Reports, Support) | UGX | 186257926 | [5 empty] | Internally Generated Funds | Direct Procurement | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2025-09-23 | 2025-10-10 | 2025-11-06 | 2025-11-13 | 2025-11-27 | 2028-11-26
6 | Design, production & supply of assorted branded items (t-shirts, mobile phone desk holders, key holders, thermos travel mini flasks, tent branding signage, pull-up banners and brochures) | UGX | 118500000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-30 | 2025-08-12 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2025-12-04
7 | Annual licenses, support and maintenance for the internal segmentation firewall (HQ & DR) | UGX | 123818522 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-06 | 2025-10-17 | 2025-11-14 | 2025-11-21 | 2025-12-05 | 2028-12-04
8 | Assorted office furniture and fittings | UGX | 107800000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-14 | 2025-11-03 | 2025-12-01 | 2025-12-08 | 2025-12-22 | 2026-02-25
9 | Window blinds for level 3 & 6 | UGX | 90000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-22 | 2025-08-04 | 2025-09-01 | 2025-09-08 | 2025-09-22 | 2025-10-22
10 | Items for donation and branding of the items for the Corporate Social Investment) | UGX | 80000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-12-18 | 2026-01-10 | 2026-01-30 | 2026-02-17 | 2026-02-28 | 2026-03-25
11 | Credit insurance cover | UGX | 64619150 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-24 | 2025-10-31 | 2025-11-24 | 2025-12-01 | 2025-12-15 | 2026-01-19
12 | IT accessories (SSD Drives) and Computer monitors | UGX | 64500000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-12-17 | 2025-12-30 | 2026-01-19 | 2026-01-29 | 2026-02-13 | 2026-03-10
13 | SurfacePro tablet devices | UGX | 60000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-09-25 | 2025-10-10 | 2025-11-07 | 2025-11-14 | 2025-11-28 | 2026-01-02
14 | Assorted branded and general stationery | UGX | 56175000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-04-29 | 2026-05-18 | 2026-06-02 | 2026-06-12 | 2026-06-26 | 2029-06-25
15 | Cleaning services and cleaning materials | UGX | 51640000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-24 | 2025-10-31 | 2025-11-24 | 2025-12-01 | 2025-12-15 | 2026-01-14
16 | Gift hampers for the Fund's Stakeholders | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-28 | 2025-11-04 | 2025-11-19 | 2025-11-26 | 2025-12-10 | 2025-12-30
17 | Magazine adverts through out the year | UGX | 50000000 | [5 empty] | Internally Generated Funds | Direct Procurement | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2026-03-27 | 2026-04-13 | 2026-05-08 | 2026-05-15 | 2026-05-30 | 2026-06-04
18 | Additional hotels services under framework | UGX | 48000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Framework Contracts | No | Yes | Local Providers | 2026-02-02 | 2026-02-13 | 2026-03-09 | 2026-03-16 | 2026-03-30 | 2029-03-29
19 | Additional office space on Level 7 | UGX | 46817256 | [5 empty] | Internally Generated Funds | Direct Procurement | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2026-02-28
20 | Website Hosting Services (Wildcard SSL certificates and maintenance services) | UGX | 45000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-30 | 2025-08-12 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2028-09-29
21 | School quiz (event production services, branding, photography, videography & live streaming, production of short promo) | UGX | 35000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-01-14 | 2026-01-27 | 2026-02-20 | 2026-02-27 | 2026-03-13 | 2026-03-31
22 | Motor Vehicle hire services under framework | UGX | 34000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Framework Contracts | No | Yes | Local Providers | 2025-07-30 | 2025-08-12 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2028-09-29
23 | Capital & capital items (portable wireless speaker, camera lens, asset tags, tyres & aerobics items) | UGX | 35470000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-02-26 | 2026-03-12 | 2026-04-09 | 2026-04-16 | 2026-04-30 | 2026-05-29
24 | Office Painting for level 6 | UGX | 30000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Special Interest Groups | 2025-07-31 | 2025-08-15 | 2025-09-04 | 2025-09-16 | 2025-09-30 | 2025-10-30
25 | Support and maintenance services for IT Equipment | UGX | 30000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Framework Contracts | No | Yes | Local Providers | 2026-05-06 | 2026-05-19 | 2026-06-05 | 2026-06-12 | 2026-06-26 | 2029-06-25
26 | ManageEngine AD Manager Plus License. | UGX | 29048930 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-01-16 | 2026-01-28 | 2026-02-12 | 2026-02-27 | 2026-03-13 | 2029-03-12
27 | Digital Out-of-Home Billboard | UGX | 28000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Special Interest Groups | 2025-10-01 | 2025-10-21 | 2025-11-14 | 2025-12-01 | 2025-12-15 | 2026-01-14
28 | Research systems licenses (SPSS, STATA) | UGX | 27237600 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-08-12 | 2025-08-25 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2028-09-29
29 | Designing, review and printing of the Annual Report for FY2024-2025 | UGX | 25000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-15 | 2025-07-16 | 2025-07-31 | 2025-08-15 | 2025-08-29 | 2025-09-18
30 | Perimeter Firewall Security Solution Support and Maintenance | UGX | 24308000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-12 | 2025-10-22 | 2025-11-11 | 2025-11-26 | 2025-12-10 | 2028-12-09
31 | Supply of Mobile phones | UGX | 24000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-02-26 | 2026-03-12 | 2026-04-09 | 2026-04-16 | 2026-04-30 | 2026-05-15
32 | Supply of office catering consumables | UGX | 22820000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-04-14 | 2026-04-21 | 2026-04-27 | 2026-05-04 | 2026-05-18 | 2026-05-29
33 | Symantec End Point Protection | UGX | 20000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-09-09 | 2025-09-24 | 2025-10-22 | 2025-11-06 | 2025-11-20 | 2028-11-19
34 | Provision of Production services (DPF song in 5 languages, graphical animated DPF video in 1 language and six short videos) | UGX | 19000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-30 | 2025-11-14 | 2025-12-04 | 2025-12-14 | 2025-12-31 | 2028-12-30
35 | Installation of intrusion system for level 6 | UGX | 16000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-09-14 | 2025-09-29 | 2025-10-27 | 2025-11-11 | 2025-11-25 | 2028-11-24
36 | Additional air conditioning units for Level 3 | UGX | 15000000 | [5 empty] | Internally Generated Funds | Direct Procurement | Supplies | Lumpsum Contracts | No | No | N/A | 2025-07-28 | 2025-08-11 | 2025-08-26 | 2025-09-10 | 2025-09-30 | 2025-10-30
37 | Board Courtesies | UGX | 14000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2025-10-02 | 2025-10-17 | 2025-11-10 | 2025-11-17 | 2025-12-01 | 2025-12-15
38 | Support and maintenance services for access control and CCTV and licenses | UGX | 13650000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-09-14 | 2025-09-29 | 2025-10-27 | 2025-11-11 | 2025-11-25 | 2028-11-24
39 | Replacement Headphones for staff | UGX | 12000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2025-07-18 | 2025-08-04 | 2025-09-01 | 2025-09-16 | 2025-09-30 | 2025-10-30
40 | Photography and videography for town hall meeting and stakeholder engagement | UGX | 11000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-03-09 | 2026-03-16 | 2026-04-09 | 2026-04-16 | 2026-04-30 | 2027-04-30
41 | DPF Logo for level 6 | UGX | 5000000 | [5 empty] | Internally Generated Funds | Quotations Method | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2025-07-30 | 2025-08-12 | 2025-09-09 | 2025-09-16 | 2025-09-30 | 2025-10-30
42 | Courier Services (distribution of calendars & gift hampers) | UGX | 5000000 | [5 empty] | Internally Generated Funds | Quotations Method | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2025-10-08 | 2025-10-23 | 2025-11-07 | 2025-11-14 | 2025-11-28 | 2025-12-15
43 | Translation services for DPF terminologies into 5 languages, lyrics into 5 languages and FAQs into 10 languages | UGX | 4550000 | [5 empty] | Internally Generated Funds | Micro Procurement | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2025-09-19 | 2025-09-26 | N/A | N/A | 2025-09-30 | 2026-01-28
44 | Supply of corporate wear | UGX | 4000000 | [5 empty] | Internally Generated Funds | Micro Procurement | Supplies | Lumpsum Contracts | No | No | Special Interest Groups | 2025-09-19 | 2025-09-26 | N/A | N/A | 2025-09-30 | 2025-10-30
| Prepared by |  | Name: | Emily Mbabazi
Signature:
|  |  | Designation: | Head PDU
Date:
| Approved by |  | Name: | Moses Apell
Signature:
|  |  | Designation: | For: Accounting Officer
Date:

## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO THE SECRETARY TO TREASURY, PPDA AND PUBLICATION
Procuring and Disposing Entity: DEPOSIT PROTECTION FUND
Financial Year: 2025/26
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) |  |  |  |  | Source of funding | Procurement method | Procurement Type | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme: Local Providers, Special Interest Groups | Contract type | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [6 empty] | Invitation of Expressions of Interest date | Closing-Opening date | Approval of shortlist | Notification date | Invitation of proposals date | Submission/ opening date | Approval of final evaluation report | Notification date | Contract signing date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25
1 | Real estate consultants (Architects, Designer and Design review & Supervisor) | UGX | 4130000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Consultancy Services | No | N/A | Lumpsum Contracts |  |  |  |  | 2026-03-13 | 2026-04-08 | 2026-05-08 | 2026-05-20 | 2026-06-19 | 2027-01-15
2 | Customer Awareness Survey consultancy | UGX | 450000000 | [5 empty] | Internally Generated Funds | Open International Bidding(OIB) | Consultancy Services | No | N/A | Lumpsum Contracts |  |  |  |  | 2025-07-24 | 2025-08-20 | 2025-09-19 | 2025-09-30 | 2025-10-30 | 2025-12-29
3 | Consultancy Services for Organisational Restructuring, Compensation and Benefits Survey | UGX | 250000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Consultancy Services | No | Local Providers | Lumpsum Contracts |  |  |  |  | 2025-08-26 | 2025-09-22 | 2025-10-16 | 2025-10-29 | 2025-11-28 | 2026-01-27
4 | Consultancy Services to review Fortinet Security Services | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | No | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-01-15 | 2026-02-04 | 2026-03-06 | 2026-03-18 | 2026-03-31 | 2026-04-20
5 | In-house board trainings and consultancies on corporate governance | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-04-01 | 2026-04-29 | 2026-05-29 | 2026-06-05 | 2026-06-22 | 2027-06-22
6 | Provision of Recruitment services under framework | UGX | 47500000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Framework Contracts |  |  |  |  | 2026-03-06 | 2026-03-31 | 2026-04-13 | 2026-04-20 | 2026-04-30 | 2029-04-29
7 | External Facilitator for ESG and Sensitization (Framework, ESG Champions, Mgt Comm and EXCO) - Q2 & Q3 | UGX | 20000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Special Interest Groups | Lumpsum Contracts |  |  |  |  | 2026-01-20 | 2026-02-09 | 2026-03-11 | 2026-03-18 | 2026-03-31 | 2026-04-30
8 | External Facilitator for Project Management | UGX | 10000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Special Interest Groups | Lumpsum Contracts |  |  |  |  | 2025-09-22 | 2025-10-17 | 2025-11-03 | 2025-11-10 | 2025-11-20 | 2026-01-19
9 | Development of the Course Structure on Deposit Insurance | UGX | 5000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Special Interest Groups | Lumpsum Contracts |  |  |  |  | 2025-10-15 | 2025-11-10 | 2025-12-10 | 2025-12-17 | 2025-12-31 | 2026-03-01
| Prepared by |  | Name: | Emily Mbabazi
Signature:
|  |  | Designation: | Head PDU
Date:
| Approved by |  | Name | Moses Apell
Signature:
|  |  | Designation: | For: Accounting Officer
Date:

## User guiding notes
Note 1
Where they have been used, the following abbreviations stand for;
PDU - Procurement and Disposal Unit
SUPS - Supplies
NCONS - Non-consultancy Services
CONS - Consultancy Services
WRKS -Works
FY - Financial Year
Note 2
There are 2 templates, the first being for supplies, works, non-consultancy services and the second being for consultancy services. All fields in the templates to be submitted should be accurately completed
Note 3
The templates for internal use are for the PDU's tracking purposes and should not be submitted
Note 4
The multi-year procurement field should only be used for procurements whose projected completion time is to exceed one FY. And where the contract is in its subsequent years of implementation, the plan should be completed to indicate the completed and pending time/funding to contract completion.
Note 5
This template should be used in line with Sections 34(2), 58 of the PPDA Act and the PPDA (Procurement Planning) Regulations, 2023
Note 6
The approved plan should be submitted to the Treasury, PPDA and published by 31st July
For any clarification about the plan template or related issues reach out on;
compliance@ppda.go.ug
or call 0414311100