## SUPS-WRKS-NCONS
PROCUREMENT PLAN FOR GOODS, WORKS AND NON CONSULTANCY SERVICES - FOR SUBMISSION TO TREASURY, PPDA and PUBLICATION
Procuring and Disposing Entity: DEPOST PROTECTION FUND
Financial Year: 2026-27
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) |  |  |  |  | Source of funding | Procurement method | Procurement Category | Contract Type | PRE-QUALIFICATION (Yes or No) | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme (Local Providers, Special Interest Groups) | INVITATION AND AWARD OF BIDS |  |  |  | Contract signing date | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [7 empty] | Bid invitation date | Bid closing/ Opening date | Approval evaluation report date | Award notification date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22
1 | Acquisition of land | UGX | 28665000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Supplies | Lumpsum Contracts | No | No | N/A | 2027-01-06 | 2027-01-21 | 2027-02-25 | 2027-03-17 | 2027-03-31 | 2027-04-30
2 | Medical Insurance Cover | UGX | 550000000 | [5 empty] | Internally Generated Funds | Open Domestic Bidding | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2026-10-07 | 2026-10-22 | 2026-11-26 | 2026-12-16 | 2026-12-30 | 2029-12-29
3 | FortiManager VM-Central Management Annual Licenses, FortiAnalyser VM-Central Management Annual Licenses, Fortinet Endpoint Security with FortiSASE Annual Subscription, FortiSASE Secure Private Access Connector License for SD-WAN and Perimeter Firewall Licenses at HQ | UGX | 309169196 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-13 | 2027-01-27 | 2027-03-03 | 2027-03-24 | 2027-04-15 | 2030-04-14
4 | Events production (public baraza, higher institutions quiz & DPF @ 10) | UGX | 304000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-12-18 | 2027-01-08 | 2027-02-12 | 2027-03-05 | 2027-03-31 | 2027-04-20
5 | Assorted IT Hardware Equipment (Surface Pro Tablet Devices, Laptops and High-Performance Laptop) | UGX | 300000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding | Supplies | Lumpsum Contracts | No | No | N/A | 2026-08-17 | 2026-09-07 | 2026-10-12 | 2026-11-02 | 2026-11-27 | 2026-12-17
6 | Design & production of branded souvenir, promotional, awareness materials & DPF @ 10 events (t-shirts, executive notebooks, spiral-bound notebooks, executive pens,standard pens, wall calendars, digital desk calendars, pull-up banners, posters, stickers, brochures in different languages, podium, corporte shirts and executive gift sets) | UGX | 339100000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-11-16 | 2026-12-07 | 2027-01-11 | 2027-02-01 | 2027-02-26 | 2027-04-02
7 | Support and Maintenance Services for the HIA System | UGX | 200000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2030-04-21
8 | Decoration, Photography, videography & livestreaming | UGX | 185770000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Framework Contracts | No | Yes | Special Interest Groups | 2026-07-27 | 2026-08-10 | 2026-08-25 | 2026-09-08 | 2026-09-18 | 2029-09-17
9 | DPPS enhancements | UGX | 171000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2027-05-12
10 | Server equipment warranties for DELL and HPE servers, Sharepoint Server SE Licenses and Exchange Server SE Licenses and 60 User CALs | UGX | 167500000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2030-04-21
11 | Assorted office furniture & fittings (window blinds for level 3 & 6, ceiling boards & balcony canopy for level 6, wall-to-wall carpet, office safe & accolades cabinet) | UGX | 156000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-08-03 | 2026-08-18 | 2026-09-02 | 2026-09-16 | 2026-09-28 | 2026-11-12
12 | ZOHO ManageEngine Service Desk Plus Annual Licenses, ManageEngine Op Manager and End Point Central Annual Licenses and Adobe Software Licenses | UGX | 120960576 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2030-04-21
13 | Primary Internet Services at the DPF HQ and DR sites | UGX | 114424128 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2030-04-21
14 | Procurement & branding of a medical incinerator for Moroto RRH (Corporate Social Investment) | UGX | 80000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-08-19 | 2026-09-11 | 2026-10-01 | 2026-10-19 | 2026-10-30 | 2026-11-24
15 | Microsoft Project Plan 3 Annual Licenses, Microsoft Visio Plan 2 Annual Licenses, Microsoft Copilot Annual Licenses and Microsoft Power BI (Developer) | UGX | 72048000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | N/A | 2027-01-15 | 2027-02-05 | 2027-03-02 | 2027-03-23 | 2027-04-22 | 2030-04-21
16 | Production of DPF animated video, song and short videos for online publicity | UGX | 71000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-09-04 | 2026-09-29 | 2026-10-19 | 2026-11-06 | 2026-11-19 | 2027-02-17
17 | CCTV and Access Control system installation on Level 6 | UGX | 70000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | N/A | 2026-08-03 | 2026-08-18 | 2026-09-02 | 2026-09-16 | 2026-09-28 | 2029-09-27
18 | Board Gifts/Souvenirs, certificates and plaques & introductory pack | UGX | 70120000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-09-04 | 2026-09-29 | 2026-10-19 | 2026-11-06 | 2026-11-19 | 2027-02-17
19 | Gift hampers for the Fund's Stakeholders | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-10-28 | 2026-11-04 | 2026-11-19 | 2026-11-26 | 2026-12-10 | 2026-12-21
20 | Billboard advertising: Digital Out-Of-Home screens (for DPF promotional Video) | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-09-04 | 2026-09-29 | 2026-10-19 | 2026-11-06 | 2026-11-19 | 2027-02-17
21 | Assorted stationery (introductory Board pack, branded & general office stationery) | UGX | 49900000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2027-03-01 | 2027-03-11 | 2027-03-31 | 2027-04-15 | 2027-04-26 | 2027-05-21
22 | Procurement and branding of concrete garden benches for Kumi & Busitema Universities | UGX | 43000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-08-17 | 2026-09-11 | 2026-10-01 | 2026-10-19 | 2026-10-30 | 2027-01-08
23 | Designing, review & printing of the annual report for FY2025-2026 | UGX | 30000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | No | N/A | 2026-08-05 | 2026-08-20 | 2026-09-04 | 2026-09-18 | 2026-09-30 | 2026-10-31
24 | Mobile phones | UGX | 28000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-07-28 | 2026-08-12 | 2026-08-27 | 2026-09-10 | 2026-09-25 | 2026-10-05
25 | Designing, review and printing of the Annual Report for FY2024-2025 | UGX | 25000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-08-14 | 2026-08-24 | 2026-09-03 | 2026-09-18 | 2026-09-30 | 2026-10-15
26 | Maintenance of plants for 3rd and 6th floors | UGX | 24000000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-10-06 | 2026-10-16 | 2026-10-28 | 2026-11-12 | 2026-11-27 | 2029-11-26
27 | Uniform & Corporate wear | UGX | 20000000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-10-26 | 2026-11-05 | 2026-11-17 | 2026-12-02 | 2026-12-17 | 2027-01-21
28 | Hotel & conference facilities for higher institutions quiz | UGX | 14500000 | [5 empty] | Internally Generated Funds | Quotation | Non-Consultancy Services | Lumpsum Contracts | No | Yes | N/A | 2027-01-11 | 2027-01-21 | 2027-02-02 | 2027-02-15 | 2027-02-25 | 2027-03-02
29 | Assorted capital & sundry items | UGX | 12350000 | [5 empty] | Internally Generated Funds | Quotation | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2026-11-17 | 2026-12-02 | 2026-12-14 | 2026-12-29 | 2027-01-13 | 2027-02-02
30 | Asset tagging | UGX | 10000000 | [5 empty] | Internally Generated Funds | Micro | Supplies | Lumpsum Contracts | No | No | N/A | 2027-04-16 | 2027-04-22 | N/A | N/A | 2027-04-29 | 2027-05-19
31 | Board courtesies | UGX | 7000000 | [5 empty] | Internally Generated Funds | Micro | Supplies | Lumpsum Contracts | No | Yes | Local Providers | 2027-02-15 | 2027-02-19 | N/A | N/A | 2027-02-26 | 2027-03-01
32 | Website Plugins | UGX | 5531341 | [5 empty] | Internally Generated Funds | Micro | Supplies | Lumpsum Contracts | No | Yes | N/A | 2027-04-12 | 2027-04-17 | N/A | N/A | 2027-04-22 | 2030-04-21
33 | Maintenance Services for PABX Equipment | UGX | 5000000 | [5 empty] | Internally Generated Funds | Micro | Non-Consultancy Services | Lumpsum Contracts | No | Yes | N/A | 2027-04-12 | 2027-04-17 | N/A | N/A | 2027-04-22 | 2030-04-21
34 | DPF Logo for level 6 | UGX | 5000000 | [5 empty] | Internally Generated Funds | Micro | Supplies | Lumpsum Contracts | No | Yes | Special Interest Groups | 2026-09-18 | 2026-09-23 | N/A | N/A | 2026-09-28 | 2026-10-28
35 | Courier Services (distribution of gift hampers) | UGX | 5000000 | [5 empty] | Internally Generated Funds | Micro | Non-Consultancy Services | Lumpsum Contracts | No | Yes | Local Providers | 2026-11-10 | 2026-11-13 | N/A | N/A | 2026-11-18 | 2026-12-08
36 | Password Manager | UGX | 4000000 | [5 empty] | Internally Generated Funds | Micro | Non-Consultancy Services | Lumpsum Contracts | No | Yes | N/A | 2027-03-22 | 2027-03-25 | N/A | N/A | 2027-04-01 | 2027-05-06
37 | Translations of DPF Frequently Asked Questions (FAQs) into 5 languages | UGX | 2600000 | [5 empty] | Internally Generated Funds | Micro | Non-Consultancy Services | Lumpsum Contracts | No | No | N/A | 2026-12-01 | 2026-12-04 | N/A | N/A | 2026-12-11 | 2027-02-09
32336973241
| Prepared by |  | Name:
Signature:
|  |  | Designation: | Head PDU
Date:
| Approved by |  | Name:
Signature:
|  |  | Designation: | Accounting Officer
Date:

## Consultancy
PROCUREMENT PLAN FOR CONSULTANCY SERVICES - FOR SUBMISSION TO THE SECRETARY TO TREASURY, PPDA AND PUBLICATION
Procuring and Disposing Entity: DEPOSIT PROTECTION FUND
Financial Year: 2026-27
S/No | Subject of procurement | Currency | Estimated cost | Multi-year procurement (where applicable) |  |  |  |  | Source of funding | Procurement method | Procurement Type | Apply Reservation Scheme (Yes/No) | Apply Reservation Scheme: Local Providers, Special Interest Groups | Contract type | Request for Expression of Interest |  |  |  | Invitation of proposals and approval for award |  |  |  |  | Completion date
|  |  |  | Current year's estimated cost | Projected completion time (in years) | Paid up sum | Pending sum | Pending time to completion | [6 empty] | Invitation of Expressions of Interest date | Closing-Opening date | Approval of shortlist | Notification date | Invitation of proposals date | Submission/ opening date | Approval of final evaluation report | Notification date | Contract signing date
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20 | Column21 | Column22 | Column23 | Column24 | Column25
1 | Consultancy for the development project & Cost Manager | UGX | 258278400 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Consultancy Services | No | N/A | Lumpsum Contracts |  |  |  |  | 2027-01-27 | 2027-02-16 | 2027-03-09 | 2027-03-21 | 2027-03-31 | 2027-06-29
2 | Consutancy Services to conduct Vulnerability Assessment and Penetration Testing (VAPT) | UGX | 250000000 | [5 empty] | Internally Generated Funds | Restricted Domestic Bidding (RDB) | Consultancy Services | No | N/A | Lumpsum Contracts |  |  |  |  | 2026-08-28 | 2026-09-17 | 2026-10-08 | 2026-10-20 | 2026-10-30 | 2026-12-31
3 | Consultancy services for Board evaluation and board induction | UGX | 110000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-07-29 | 2026-08-18 | 2026-09-08 | 2026-09-20 | 2026-09-30 | 2026-12-01
4 | Consultancy for the DPF's ESG implementation & sustainability reporting | UGX | 89680000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-12-03 | 2026-12-18 | 2027-01-08 | 2027-01-19 | 2027-01-29 | 2027-03-31
5 | Consultancy for Formulation of the Strategy for 2027-2032 | UGX | 80000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-10-02 | 2026-10-19 | 2026-11-09 | 2026-11-20 | 2026-11-30 | 2027-01-29
6 | Consultancy Services for External Quality Assessment to check compliance with Global International Audit Standards (GIAS) | UGX | 50000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | Yes | Local Providers | Lumpsum Contracts |  |  |  |  | 2026-12-03 | 2026-12-18 | 2027-01-08 | 2027-01-19 | 2027-01-29 | 2027-03-31
7 | In-house Board training and consultancies in corporate governance | UGX | 30000000 | [5 empty] | Internally Generated Funds | Quotations Method | Consultancy Services | No | N/A | Lumpsum Contracts |  |  |  |  | 2026-12-04 | 2026-12-19 | 2027-01-09 | 2027-01-20 | 2027-01-30 | 2027-04-01
867958400
| Prepared by |  | Name: | [11 empty] | Approved by | Name
|  |  | Signature: | [12 empty] | Signature:
|  |  | Designation: | [12 empty] | Designation:
|  |  | Date: | [12 empty] | Date:

## User guiding notes
Note 1
Where they have been used, the following abbreviations stand for;
PDU - Procurement and Disposal Unit
SUPS - Supplies
NCONS - Non-consultancy Services
CONS - Consultancy Services
WRKS -Works
FY - Financial Year
Note 2
There are 2 templates, the first being for supplies, works, non-consultancy services and the second being for consultancy services. All fields in the templates to be submitted should be accurately completed
Note 3
The templates for internal use are for the PDU's tracking purposes and should not be submitted
Note 4
The multi-year procurement field should only be used for procurements whose projected completion time is to exceed one FY. And where the contract is in its subsequent years of implementation, the plan should be completed to indicate the completed and pending time/funding to contract completion.
Note 5
This template should be used in line with Sections 34(2), 58 of the PPDA Act and the PPDA (Procurement Planning) Regulations, 2023
Note 6
The approved plan should be submitted to the Treasury, PPDA and published by 31st July
For any clarification about the plan template or related issues reach out on;
compliance@ppda.go.ug
or call 0414311100